## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Project Setup & Environment | Common | Dev Team | Initialize backend and frontend projects, configure environment variables, and ensure both run locally. Setup Git repository structure and basic scripts. | Tuấn, Danh | Done | iter1
2 | Database Design (ERD + Schema) | Database | Admin/Dev Team | Design database tables and relationships for devices, rooms, users, borrow requests, and tickets. Prepare schema for implementation and future migrations. | Tuấn, Danh | Done | iter1
3 | Base UI Layout & Routing | UI | All Roles | Build the main layout (sidebar/header) and set up routing for key pages. Ensure a consistent navigation structure across roles. | Mỹ, Vân Anh, Thảo | Done | iter1
4 | Authentication (Login/Logout) | Authentication | All Roles | Users can sign in using email/password or Google OAuth, and sign out to clear tokens/session. On successful login, redirect user based on role and store auth state securely. | Danh | Done | iter1
5 | Device List Page | Device | All | Display a list of devices with basic info (name, category, room, status). Provide navigation to details/actions depending on role. | Danh | Done | iter2 | iter2-update | Bổ sung QR code cho thiết bị; hỗ trợ scan để auto-fill report
6 | Device Search & Filter | Device | All | Enable searching by keyword and filtering by category, room, and device status. Filtering should update the list results clearly. | Mỹ | To Do | iter2 | iter2-update | Filter sẽ dùng chung cho Borrow + Equipment list; cần hỗ trợ real-time UI
7 | Submit Borrow Request | Borrow Request | Student | Student selects a device and submits a borrow request with required details (time/notes). The request is created with “Pending” status. | Thảo | Doing | iter2 | iter2-update | Borrow flow phụ thuộc session (lecturer check-in); thêm constraint chỉ mượn khi session active
8 | Cancel Borrow Request (Before Approval) | Borrow Request | Student | Student can cancel a pending request before it is approved. System updates the request status to “Cancelled”. | Thảo | Doing | iter2 | iter2-update | Cancel request cần check thêm trạng thái session + borrow constraint
9 | Approve/Reject Borrow Requests | Approval | Lecturer | Lecturer views requests for assigned class and approves or rejects them. System updates request status and records lecturer decision. | Tuấn | Doing | iter2 | iter2-update | Approval flow mở rộng: sau approve → tạo handover form
10 | Confirm Hand-over (Receiving Device) | Handover | Student, Lecturer/Technician | Confirm that the device has been handed over to the student. System updates request status to “Borrowing” and locks device availability. | Mỹ | Doing | iter2 | iter2-update | Handover flow nâng cấp: thêm checklist + upload ảnh + student confirm
11 | Return Device | Return | Student, Lecturer/Technician | Student returns the device and the staff confirms the return. System marks request as “Returned” and updates device availability. | Vân Anh | Doing | iter2 | iter2-update | Return flow nâng cấp: thêm return form + ảnh + lecturer confirm
12 | Password Management (Forgot/Reset/Change) | Authentication | All Roles | Users can request a password reset via email (reset link/OTP), set a new password, and change password while logged in. Validate password strength and display clear success/error messages. | Danh | Doing | iter3
13 | Borrow History / Personal Schedule | Borrow Request | Student | Student views personal borrow history and current requests. Include key statuses (Pending/Approved/Borrowing/Returned/Rejected). | Tuấn | To Do | iter3 | iter3-update | Tách thành My History (report + borrow), không còn chỉ borrow
14 | View Device Status by Room | Device Monitoring | Lecturer | Lecturer can view device status grouped by classroom/room. Helps track availability and usage per room. | Danh | To Do | iter3 | iter3-update | Mở rộng thành session equipment overview (real-time theo lớp)
15 | Report Broken Device During Class | Ticketing | Lecturer | Lecturer submits a ticket to report a broken device during teaching. Ticket includes device, issue description, and status “New”. | Thảo | To Do | iter3 | iter3-update | Thay bằng Guest Report Page + dùng chung cho all roles
16 | Ticket List (Broken Reports) | Ticketing | Technician | Technician views all broken-device tickets and their statuses. Provide quick access to ticket details and actions. | Mỹ | To Do | iter3 | iter3-update | Ticket list → đổi thành Report Management (có priority + AI)
17 | Approve/Reject Broken Ticket | Ticketing | Technician | Technician reviews a ticket and approves/rejects it for repair processing. Record decision and update ticket status accordingly. | Vân Anh | To Do | iter3 | iter3-update | Approve ticket → thêm assign technician + priority handling
18 | Update Ticket After Repair | Ticketing | Technician | After repair, technician updates ticket status and adds repair notes. Device condition may also be updated based on the repair result. | Vân Anh | To Do | iter3 | iter3-update | Update ticket → thêm repair tracking + condition update
19 | Device Management (CRUD) | Device Admin | Technician/Admin | Technician/Admin can add, edit, delete device records and update core fields (name, category, condition, status). Maintain consistency with room assignment. | Tuấn | To Do | iter4 | iter4-update | Thêm QR generation khi tạo device
20 | Assign Device to Room/Lab/Building | Device Admin | Technician | Assign devices to rooms/labs/buildings to reflect real location. Ensure device list and monitoring screens show updated location. | Mỹ | To Do | iter4 | iter4-update | Mapping với QR + report auto-fill
21 | User Account Management | Admin | Admin | Admin can create, edit, and delete user accounts and assign roles (Student/Lecturer/Technician/Admin). Ensure basic validation and management flow. | Tuấn | To Do | iter4
22 | Dashboard & Overall Statistics | Reporting | Admin | Provide summary metrics (total devices, available/borrowing/broken, requests by status). Visualize key numbers for admin overview. | Tuấn | To Do | iter4 | iter4-update | Dashboard mở rộng: thêm MTTR, report stats, technician performance
23 | AI Chatbot Assistant | Chatbot | All Roles | Provide an in-app chatbot to answer common questions and guide users through key workflows (borrow/return devices, request status). Suggest relevant actions/pages and basic troubleshooting tips. | Vân Anh | To Do | iter4 | iter4-update | Chatbot có thể dùng AI + gợi ý workflow

## Iter1
Iteration Tracking - Iteration 1 : Foundation
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Project Setup & Environment | Common | Initialize backend and frontend projects, configure environment variables, and ensure both run locally. Setup Git repository structure and basic scripts. | Tuấn, Danh | Done | N/A | N/A | Backend & frontend run successfully in local environment; repository structure and scripts set up.
2 | Database Design (ERD + Schema) | Database | Design database tables and relationships for devices, rooms, users, borrow requests, and tickets. Prepare schema for implementation and future migrations. | Tuấn, Danh | Done | N/A | N/A | ERD/schema drafted; core entities and relationships defined; ready for implementation/migration in next iteration.
3 | Base UI Layout & Routing | UI | Build the main layout (sidebar/header) and set up routing for key pages. Ensure a consistent navigation structure across roles. | Mỹ, Vân Anh, Thảo | Done | N/A | N/A | Base layout completed; routing skeleton created for main pages; navigation structure consistent across roles.
4 | Authentication (Login/Logout) | Authentication | Users can sign in using email/password or Google OAuth, and sign out to clear tokens/session. On successful login, redirect user based on role and store auth state securely. | Danh | Done | N/A | N/A | Login/Logout flow completed; auth state stored and cleared correctly; role-based redirect implemented (basic).
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2 : Core Borrow Flow
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes | Updated Notes
1 | Device List Page | Device | Display a list of devices with basic info (name, category, room, status). Provide navigation to details/actions depending on role. | Danh | Done | N/A | N/A | Device list screen implemented and showing device data; basic navigation/actions prepared by role. | Thêm QR code support trong device list (hiển thị + scan entry)
2 | Device Search & Filter | Device | Enable searching by keyword and filtering by category, room, and device status. Filtering should update the list results clearly. | Vân Anh | To Do | N/A | N/A | Planned for Iter 2 but not started yet; will implement filter UI + query parameters for API. | Filter sẽ dùng lại cho Borrow Equipment page
3 | Submit Borrow Request | Borrow Request | Student selects a device and submits a borrow request with required details (time/notes). The request is created with “Pending” status. | Thảo | Doing | N/A | N/A | Borrow request flow in progress; create request endpoint/UI being integrated and tested. | Borrow request phải check: session active + lecturer check-in
4 | Cancel Borrow Request (Before Approval) | Borrow Request | Student can cancel a pending request before it is approved. System updates the request status to “Cancelled”. | Thảo | Doing | N/A | N/A | Cancel request feature in progress; requires status check (only pending) and UI action confirmation. | Cancel request phải check thêm session state
5 | Approve/Reject Borrow Requests | Approval | Lecturer views requests for assigned class and approves or rejects them. System updates request status and records lecturer decision. | Tuấn | Doing | N/A | N/A | Approval flow in progress; working on request list for lecturer and status update logic. | Approval flow thêm bước tạo handover form
6 | Confirm Hand-over (Receiving Device) | Handover | Confirm that the device has been handed over to the student. System updates request status to “Borrowing” and locks device availability. | Mỹ | Doing | N/A | N/A | Not started; depends on completing approval flow and device availability update rules. | Handover flow now checklist, image upload, and student confirmation step.
7 | Return Device | Return | Student returns the device and the staff confirms the return. System marks request as “Returned” and updates device availability. | Vân Anh | Doing | N/A | N/A | Return flow in progress; will update request status to Returned and set device back to Available. | Return flow includes return form, image upload, and lecturer confirmation; support dispute handling.
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3 : Monitoring + Ticketing
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes | Updated Notes
1 | Borrow History / Personal Schedule | Borrow Request | Student views personal borrow history and current requests. Include key statuses (Pending/Approved/Borrowing/Returned/Rejected). | Tuấn | To Do | N/A | N/A | Planned: build history page + API to list requests by student; include status badges and basic filters (current vs past). | History đổi thành My History (report + borrow/approval)
2 | View Device Status by Room | Device Monitoring | Lecturer can view device status grouped by classroom/room. Helps track availability and usage per room. | Danh | To Do | N/A | N/A | Planned: implement room-based grouping screen + API query by room; show counts per status (Available/Borrowing/Broken/Maintenance). | Device monitoring chuyển thành session-based real-time tracking
3 | Report Broken Device During Class | Ticketing | Lecturer submits a ticket to report a broken device during teaching. Ticket includes device, issue description, and status “New”. | Thảo | To Do | N/A | N/A | Planned: create ticket form (device + description) and backend endpoint to create ticket with default status “New”. | Replaced by unified Report System (Guest + QR scan + manual form + AI priority).
4 | Ticket List (Broken Reports) | Ticketing | Technician views all broken-device tickets and their statuses. Provide quick access to ticket details and actions. | Mỹ | To Do | N/A | N/A | Planned: build ticket list page for technician with status column and quick actions (view/update). | Ticket list replaced by report management with priority and filtering.
5 | Approve/Reject Broken Ticket | Ticketing | Technician reviews a ticket and approves/rejects it for repair processing. Record decision and update ticket status accordingly. | Vân Anh | To Do | N/A | N/A | Planned: add approve/reject actions; store decision and update ticket status (e.g., Approved/Rejected). | Added technician assignment and priority-based handling.
6 | Update Ticket After Repair | Ticketing | After repair, technician updates ticket status and adds repair notes. Device condition may also be updated based on the repair result. | Vân Anh | To Do | N/A | N/A | Planned: implement update ticket flow (status + repair notes) and update device condition if needed (Good/Broken/Maintenance). | Added repair tracking, status flow, and device condition update.
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4 : Admin + Reporting + Optional AI
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes | Update details
| Device Management (CRUD) | Device Admin | Technician/Admin can add, edit, delete device records and update core fields (name, category, condition, status). Maintain consistency with room assignment. | Tuấn | To Do | N/A | N/A | Planned: implement device CRUD (UI + API) with validation; ensure updates reflect in device list and monitoring pages. | Updated: Generate QR code automatically when creating device; used for report scanning.
2 | Assign Device to Room/Lab/Building | Device Admin | Assign devices to rooms/labs/buildings to reflect real location. Ensure device list and monitoring screens show updated location. | Mỹ | To Do | N/A | N/A | Planned: build assignment flow (select device + select room) and update DB; verify device list shows correct location. | Updated: QR used for report auto-fill (equipment info).
3 | User Account Management | Admin | Admin can create, edit, and delete user accounts and assign roles (Student/Lecturer/Technician/Admin). Ensure basic validation and management flow. | Tuấn | To Do | N/A | N/A | Planned: implement user CRUD + role assignment; add basic input validation and access control (admin-only pages). | Updated: Added user penalty system (Warning/Restricted/Blacklisted).
4 | Dashboard & Overall Statistics | Reporting | Provide summary metrics (total devices, available/borrowing/broken, requests by status). Visualize key numbers for admin overview. | Tuấn | To Do | N/A | N/A | Planned: create dashboard summary API + UI cards/charts; include counts by device status and request status. | Updated: Dashboard extended with MTTR, report analytics, technician performance.
5 | AI Chatbot Assistant | Chatbot | Provide an in-app chatbot to answer common questions and guide users through key workflows (borrow/return devices, request status). Suggest relevant actions/pages and basic troubleshooting tips. | Vân Anh | To Do | N/A | N/A | Planned: implement FAQ-style chatbot UI; provide predefined answers and quick links to related pages (optional AI integration if time allows). | Updated: Chatbot can integrate AI for smart suggestions and workflows.
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document